## Sprint Backlog
Story No. | Story Description | Task | Estimated Effort (Hours) | Priority | Status
UHM-US-01 | As a citizen, I want to register my personal details and healthcare interests so that I can access healthcare outreach services and receive relevant notifications. | Implement notification service Create templates Trigger event notifications Integrate email/SMS Handle failures Test notification delivery | 12 | High | Not Started
UHM-US-02 | As a hospital administrator, I want to register my healthcare institution so that I can manage camps and outreach activities. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
UHM-US-03 | As an inventory administrator, I want to register and manage healthcare resource information so that inventory activities can be monitored. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 8 | Medium | Not Started
UHM-US-04 | As a registered user, I want to securely authenticate myself so that I can access authorized platform functionalities. | Design registration/profile screens Implement registration/profile APIs Validate user inputs Persist user information Implement authentication/authorization Test registration and profile management | 12 | High | Not Started
MCM-US-01 | As a hospital administrator, I want to create specialist medical camps so that healthcare services can reach underserved communities. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 16 | High | Not Started
MCM-US-02 | As a hospital administrator, I want to publish approved camps so that eligible citizens can discover and participate in them. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
MCM-US-03 | As a hospital administrator, I want to manage camp schedules so that operational changes can be communicated effectively. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | Medium | Not Started
MCM-US-04 | As a hospital administrator, I want to track camp participation so that outreach effectiveness can be measured. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | Medium | Not Started
CDB-US-01 | As a citizen, I want to discover nearby healthcare camps so that I can access relevant healthcare services. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
CDB-US-02 | As a citizen, I want personalized camp recommendations so that I can find healthcare services matching my needs. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 16 | High | Not Started
CDB-US-03 | As a citizen, I want to receive notifications about upcoming camps so that I do not miss healthcare opportunities. | Implement notification service Create templates Trigger event notifications Integrate email/SMS Handle failures Test notification delivery | 12 | High | Not Started
CDB-US-04 | As a citizen, I want to book camp appointments so that my participation can be planned in advance. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 12 | High | Not Started
CDB-US-05 | As a citizen, I want appointment confirmations so that I have details of my booking. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | Medium | Not Started
PSR-US-01 | As a camp coordinator, I want to verify patient check-ins so that attendance can be recorded accurately. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
PSR-US-02 | As a healthcare professional, I want to record screening information so that patient assessments are documented. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 16 | High | Not Started
PSR-US-03 | As a doctor, I want to maintain digital patient medical records so that healthcare information is available for future reference. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 16 | High | Not Started
PSR-US-04 | As a doctor, I want to generate referrals so that patients can receive advanced consultation or treatment. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
PSR-US-05 | As a patient navigator, I want to track referral status so that patients receive timely care. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
PSR-US-06 | As a patient navigator, I want to manage patient follow-ups so that treatment continuity is maintained. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 16 | High | Not Started
PCC-US-01 | As a healthcare professional, I want to generate digital prescriptions so that medication information is documented accurately. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | Medium | Not Started
PCC-US-02 | As a healthcare provider, I want to monitor treatment progress so that patient outcomes can be improved. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | Medium | Not Started
HDA-US-01 | As a hospital administrator, I want to analyze regional healthcare demand so that outreach planning can be improved. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 16 | High | Not Started
HDA-US-02 | As a hospital administrator, I want camp performance analytics so that outreach effectiveness can be evaluated. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
HDA-US-03 | As a hospital administrator, I want patient conversion analysis so that referral effectiveness can be measured. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
HDA-US-04 | As a hospital administrator, I want expansion opportunity insights so that future growth decisions can be supported. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 16 | High | Not Started
CRM-US-01 | As an inventory administrator, I want to register critical healthcare resources so that inventories can be managed effectively. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 12 | High | Not Started
CRM-US-02 | As an inventory administrator, I want to maintain inventory details so that resource information remains accurate. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 16 | High | Not Started
CRM-US-03 | As an inventory administrator, I want visibility into available resources so that informed decisions can be made. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 16 | High | Not Started
CRM-US-04 | As an inventory administrator, I want expiry monitoring so that resource wastage can be minimized. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 12 | High | Not Started
CRM-US-05 | As an inventory administrator, I want alerts for critical inventory situations so that immediate action can be taken. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 12 | Medium | Not Started
RRM-US-01 | As a healthcare facility administrator, I want to request critical resources so that shortages can be addressed quickly. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
RRM-US-02 | As a healthcare facility administrator, I want resource matching so that available resources can be identified. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 16 | High | Not Started
RRM-US-03 | As a healthcare facility administrator, I want to manage transfer requests so that resources can be redistributed efficiently. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 16 | High | Not Started
RRM-US-04 | As an authorized administrator, I want to approve redistribution requests so that transfers are controlled properly. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
RRM-US-05 | As a healthcare facility administrator, I want to track resource movement so that transfer status remains visible. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | Medium | Not Started
RA-US-01 | As an administrator, I want operational reports so that healthcare activities can be monitored effectively. | Design reports/dashboard Implement analytics APIs Aggregate data Display metrics Export reports Test reporting | 12 | High | Not Started
RA-US-02 | As an administrator, I want resource utilization reports so that wastage reduction efforts can be measured. | Design reports/dashboard Implement analytics APIs Aggregate data Display metrics Export reports Test reporting | 12 | High | Not Started
RA-US-03 | As an administrator, I want performance monitoring dashboards so that key healthcare metrics can be tracked. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
RA-US-04 | As a system administrator, I want centralized dashboards so that platform-wide operations can be monitored effectively. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-UM-01 | As a patient, I want to register an account so that I can access healthcare services online. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-UM-02 | As a patient, I want to securely log in to the system so that I can manage my appointments and prescriptions. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | High | Not Started
US-UM-03 | As a doctor, I want to create and update my profile so that patients can view my specialization and availability. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-UM-04 | As a hospital administrator, I want to manage hospital resources and users so that operations run efficiently. | Design registration/profile screens Implement registration/profile APIs Validate user inputs Persist user information Implement authentication/authorization Test registration and profile management | 16 | High | Not Started
US-UM-05 | As a pharmacy representative, I want to manage medicine inventory and orders so that patients receive medicines promptly. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 16 | High | Not Started
US-UM-06 | As a system administrator, I want users to access only authorized functionalities based on their roles so that data security is maintained. | Design registration/profile screens Implement registration/profile APIs Validate user inputs Persist user information Implement authentication/authorization Test registration and profile management | 16 | High | Not Started
US-AP-01 | As a patient, I want to search for hospitals, departments, and doctors so that I can find suitable healthcare providers. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
US-AP-02 | As a patient, I want to view real-time appointment slots so that I can select a convenient time. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | High | Not Started
US-AP-03 | As a patient, I want to book appointments online so that I can consult doctors without visiting the hospital. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
US-AP-04 | As a patient, I want to reschedule appointments so that I can adjust my healthcare visits when necessary. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | Medium | Not Started
US-AP-05 | As a patient, I want to cancel appointments so that I can avoid unnecessary bookings. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 6 | Medium | Not Started
US-AP-06 | As a doctor, I want to update my availability schedule so that patients can book accurate appointment slots. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | High | Not Started
US-AP-07 | As a hospital administrator, I want to manage doctor schedules centrally so that appointment conflicts are minimized. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
US-AP-08 | As a patient, I want to receive appointment reminders so that I do not miss scheduled consultations. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 6 | Medium | Not Started
US-ER-01 | As a hospital administrator, I want the system to detect doctor unavailability automatically so that disruptions can be handled quickly. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
US-ER-02 | As a patient, I want the system to find doctors with similar specializations so that my consultation can continue without delay. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-ER-03 | As a patient, I want appointments to be reassigned automatically when my doctor is unavailable so that I receive timely care. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 16 | High | Not Started
US-ER-04 | As a patient, I want to receive immediate notifications about appointment changes so that I can plan accordingly. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | High | Not Started
US-ER-05 | As a patient, I want to accept the reassigned appointment or request another slot so that I retain scheduling flexibility. | Design appointment booking screens Implement booking APIs Slot availability validation Appointment persistence Cancellation/reschedule logic Test appointment flow | 8 | Medium | Not Started
US-ER-06 | As a hospital administrator, I want reallocation records to be stored so that appointment changes can be audited. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 6 | Medium | Not Started
US-MM-01 | As a pharmacy representative, I want to receive digital prescriptions from patients so that medicine orders can be processed quickly. | Design medicine ordering module Implement pharmacy APIs Medicine availability integration Order processing Delivery status updates Test pharmacy workflow | 12 | High | Not Started
US-MM-02 | As a patient, I want the system to check medicine availability across pharmacies so that I can obtain prescribed medicines easily. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-MM-03 | As a patient, I want to view nearby pharmacies with available stock so that I can choose the most convenient option. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 8 | Medium | Not Started
US-MM-04 | As a patient, I want medicines to be reserved immediately after prescription upload so that stock is not exhausted before purchasing. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-MM-05 | As a pharmacy representative, I want orders to be generated automatically from prescriptions so that processing becomes efficient. | Design medicine ordering module Implement pharmacy APIs Medicine availability integration Order processing Delivery status updates Test pharmacy workflow | 12 | High | Not Started
US-MD-01 | As a patient, I want to order medicines online so that I can receive them without visiting a pharmacy. | Design medicine ordering module Implement pharmacy APIs Medicine availability integration Order processing Delivery status updates Test pharmacy workflow | 16 | High | Not Started
US-MD-02 | As a pharmacy representative, I want delivery partners to be assigned automatically so that deliveries are processed efficiently. | Design medicine ordering module Implement pharmacy APIs Medicine availability integration Order processing Delivery status updates Test pharmacy workflow | 12 | High | Not Started
US-MD-03 | As a patient, I want to know the estimated time of medicine delivery so that I know when my order will arrive. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 12 | High | Not Started
US-MD-04 | As a patient, I want updates on delivery progress so that I remain informed throughout the process. | Analyze requirements Design UI/API Implement business logic Database integration Validation & exception handling Unit testing | 8 | Medium | Not Started
US-EC-01 | As an ambulance operator, I want to locate nearby hospitals during emergencies so that patients can receive care quickly. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
US-EC-02 | As an ambulance operator, I want to view ICU, ventilator, and emergency ward availability so that appropriate hospitals can be selected. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 16 | High | Not Started
US-EC-03 | As an ambulance operator, I want the system to recommend the best hospital based on resources, distance, and specialists so that emergency response is optimized. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 16 | High | Not Started
US-EC-04 | As a hospital administrator, I want specialist availability to be verified before patient transfer so that treatment of readiness is ensured. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | High | Not Started
US-EC-05 | As an ambulance operator, I want to reserve emergency admission before patient arrival so that treatment can begin immediately upon reaching the hospital. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 16 | High | Not Started
US-SV-01 | As a hospital administrator, I want to track specialist duty schedules so that specialist availability can be monitored accurately. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 8 | Medium | Not Started
US-SV-02 | As a hospital administrator, I want to receive alerts when specialists become unavailable so that alternative arrangements can be made. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 8 | Medium | Not Started
US-SV-03 | As an ambulance operator, I want the system to notify the specialist when an emergency case comes up. | Design ambulance request module Implement dispatch APIs Hospital/resource lookup Status tracking Notification integration Test emergency workflow | 12 | Medium | Not Started
US-CS-01 | As a user, I want to receive notifications through SMS, email, and push notifications so that I stay informed about appointments, emergencies, medicine availability, and deliveries. | Design registration/profile screens Implement registration/profile APIs Validate user inputs Persist user information Implement authentication/authorization Test registration and profile management | 12 | Medium | Not Started
US-CS-02 | As a user, I want to receive emergency alerts during critical situations so that I can take immediate action. | Design registration/profile screens Implement registration/profile APIs Validate user inputs Persist user information Implement authentication/authorization Test registration and profile management | 12 | High | Not Started
US-RA-01 | As a hospital administrator, I want to generate appointment statistics reports so that service demand and appointment trends can be analyzed. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | Medium | Not Started
US-RA-02 | As a hospital administrator, I want to generate doctor utilization reports so that healthcare resources can be optimized. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | Medium | Not Started
US-RA-03 | As a pharmacy representative, I want to generate inventory reports so that medicine stock levels can be monitored effectively. | Design inventory management module Implement inventory APIs CRUD resource records Validate inventory data Database integration Test inventory functions | 12 | Medium | Not Started
US-RA-04 | As a hospital administrator, I want to analyze emergency response metrics so that emergency services can be improved. | Design hospital registration module Implement hospital APIs Validate hospital details Store hospital records Role-based access Test registration workflow | 12 | Medium | Not Started
US-RA-05 | As a pharmacy representative, I want to generate medicine delivery performance reports so that delivery efficiency can be evaluated. | Design medicine ordering module Implement pharmacy APIs Medicine availability integration Order processing Delivery status updates Test pharmacy workflow | 12 | Medium | Not Started