## Sheet1
1. User Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
User Registration | US-UM-01 | As a patient, I want to register an account so that I can access healthcare services online. | User can register with valid details and receive confirmation. | 5 | High
Patient Login | US-UM-02 | As a patient, I want to securely log in to the system so that I can manage my appointments and prescriptions. | User can log in with valid credentials. | 3 | High
Doctor Profile Management | US-UM-03 | As a doctor, I want to create and update my profile so that patients can view my specialization and availability. | Doctor profile can be created and updated. | 5 | High
Hospital Administrator Management | US-UM-04 | As a hospital administrator, I want to manage hospital resources and users so that operations run efficiently. | Admin can manage users and resources. | 8 | High
Pharmacy Management | US-UM-05 | As a pharmacy representative, I want to manage medicine inventory and orders so that patients receive medicines promptly. | Pharmacy can update inventory and orders. | 8 | High
Role-Based Access Control | US-UM-06 | As a system administrator, I want users to access only authorized functionalities based on their roles so that data security is maintained. | Role-based access is enforced. | 8 | High
2. Appointment Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Search Healthcare Services | US-AP-01 | As a patient, I want to search for hospitals, departments, and doctors so that I can find suitable healthcare providers. | Search results are displayed correctly. | 5 | High
View Available Slots | US-AP-02 | As a patient, I want to view real-time appointment slots so that I can select a convenient time. | Available slots are displayed in real time. | 3 | High
Book Appointment | US-AP-03 | As a patient, I want to book appointments online so that I can consult doctors without visiting the hospital. | Appointment is booked successfully. | 5 | High
Reschedule Appointment | US-AP-04 | As a patient, I want to reschedule appointments so that I can adjust my healthcare visits when necessary. | Appointment can be rescheduled. | 3 | Medium
Cancel Appointment | US-AP-05 | As a patient, I want to cancel appointments so that I can avoid unnecessary bookings. | Appointment cancellation is successful. | 2 | Medium
Update Doctor Availability | US-AP-06 | As a doctor, I want to update my availability schedule so that patients can book accurate appointment slots. | Schedule updates are reflected instantly. | 3 | High
Manage Doctor Schedules | US-AP-07 | As a hospital administrator, I want to manage doctor schedules centrally so that appointment conflicts are minimized. | Admin can manage doctor schedules. | 5 | High
Appointment Reminders | US-AP-08 | As a patient, I want to receive appointment reminders so that I do not miss scheduled consultations. | Reminder notifications are sent. | 2 | Medium
3. Emergency Appointment Reallocation
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Detect Doctor Unavailability | US-ER-01 | As a hospital administrator, I want the system to detect doctor unavailability automatically so that disruptions can be handled quickly. | Unavailability is detected automatically. | 5 | High
Identify Alternative Doctors | US-ER-02 | As a patient, I want the system to find doctors with similar specializations so that my consultation can continue without delay. | Alternative doctors are suggested. | 5 | High
Automatic Appointment Reassignment | US-ER-03 | As a patient, I want appointments to be reassigned automatically when my doctor is unavailable so that I receive timely care. | Appointment is reassigned automatically. | 8 | High
Instant Patient Notification | US-ER-04 | As a patient, I want to receive immediate notifications about appointment changes so that I can plan accordingly. | Notifications are delivered instantly. | 3 | High
Patient Approval for Reallocation | US-ER-05 | As a patient, I want to accept the reassigned appointment or request another slot so that I retain scheduling flexibility. | Patient can approve or reject reassignment. | 3 | Medium
Reallocation History Maintenance | US-ER-06 | As a hospital administrator, I want reallocation records to be stored so that appointment changes can be audited. | Reallocation history is maintained. | 2 | Medium
4. Medicine Availability Management
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Receive Digital Prescriptions | US-MM-01 | As a pharmacy representative, I want to receive digital prescriptions from patients so that medicine orders can be processed quickly. | Digital prescriptions are received successfully. | 5 | High
Check Medicine Availability | US-MM-02 | As a patient, I want the system to check medicine availability across pharmacies so that I can obtain prescribed medicines easily. | Medicine availability is displayed correctly. | 5 | High
Display Nearby Pharmacies | US-MM-03 | As a patient, I want to view nearby pharmacies with available stock so that I can choose the most convenient option. | Nearby pharmacies are displayed correctly. | 3 | Medium
Medicine Reservation | US-MM-04 | As a patient, I want medicines to be reserved immediately after prescription upload so that stock is not exhausted before purchasing. | Medicine reservation is completed successfully. | 5 | High
Pharmacy Order Generation | US-MM-05 | As a pharmacy representative, I want orders to be generated automatically from prescriptions so that processing becomes efficient. | Pharmacy orders are generated successfully. | 5 | High
5. Medicine Delivery System
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Online Medicine Ordering | US-MD-01 | As a patient, I want to order medicines online so that I can receive them without visiting a pharmacy. | Order is placed successfully. | 8 | High
Delivery Partner Assignment | US-MD-02 | As a pharmacy representative, I want delivery partners to be assigned automatically so that deliveries are processed efficiently. | Delivery partner is assigned automatically. | 5 | High
Estimated Delivery Time | US-MD-03 | As a patient, I want to know the estimated time of medicine delivery so that I know when my order will arrive. | Order tracking updates are displayed in real time. | 5 | High
Delivery Notifications | US-MD-04 | As a patient, I want updates on delivery progress so that I remain informed throughout the process. | Delivery notifications are sent successfully. | 3 | Medium
6. Emergency Hospital Co-ordination
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Nearby Hospital Discovery | US-EC-01 | As an ambulance operator, I want to locate nearby hospitals during emergencies so that patients can receive care quickly. | Nearby hospitals are displayed based on location. | 5 | High
Emergency Resource Availability | US-EC-02 | As an ambulance operator, I want to view ICU, ventilator, and emergency ward availability so that appropriate hospitals can be selected. | ICU, ventilator, and emergencyv ward availbaility is displayed. | 8 | High
Hospital Recommendation System | US-EC-03 | As an ambulance operator, I want the system to recommend the best hospital based on resources, distance, and specialists so that emergency response is optimized. | Recommended hospitals are ranked based on availability and proximity. | 8 | High
Specialist Availability Verification | US-EC-04 | As a hospital administrator, I want specialist availability to be verified before patient transfer so that treatment of readiness is ensured. | Nearby hospitals are displayed based on location. | 5 | High
Emergency Pre-Booking | US-EC-05 | As an ambulance operator, I want to reserve emergency admission before patient arrival so that treatment can begin immediately upon reaching the hospital. | Nearby hospitals are displayed based on location. | 8 | High
7. Specialist Availability Verification
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Specialist Duty Schedule Tracking | US-SV-01 | As a hospital administrator, I want to track specialist duty schedules so that specialist availability can be monitored accurately. | Specialist schedules are displayed accurately. | 3 | Medium
Specialist Unavailability Alert | US-SV-02 | As a hospital administrator, I want to receive alerts when specialists become unavailable so that alternative arrangements can be made. | Specialist schedules are displayed accurately. | 3 | Medium
Specialist Notification | US-SV-03 | As an ambulance operator, I want the system to notify the specialist when an emergency case comes up. | Specialist schedules are displayed accurately. | 5 | Medium
8. Communication Systems
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Notification Management | US-CS-01 | As a user, I want to receive notifications through SMS, email, and push notifications so that I stay informed about appointments, emergencies, medicine availability, and deliveries. | Notifications are sent successfully through SMS, email, and push channels. | 5 | Medium
Emergency Alert Management | US-CS-02 | As a user, I want to receive emergency alerts during critical situations so that I can take immediate action. | Emergency alerts are delivered instantly to users. | 5 | High
9. Results and Analysis
Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority
Appointment Statistics Reporting | US-RA-01 | As a hospital administrator, I want to generate appointment statistics reports so that service demand and appointment trends can be analyzed. | Appointment reports are generated accurately. | 5 | Medium
Doctor Utilization Reporting | US-RA-02 | As a hospital administrator, I want to generate doctor utilization reports so that healthcare resources can be optimized. | Doctor utilization reports are generated accurately. | 5 | Medium
Pharmacy Inventory Reporting | US-RA-03 | As a pharmacy representative, I want to generate inventory reports so that medicine stock levels can be monitored effectively. | Inventory reports display correct stock information. | 5 | Medium
Emergency Response Metrics Reporting | US-RA-04 | As a hospital administrator, I want to analyze emergency response metrics so that emergency services can be improved. | Emergency response metrics are reported accurately. | 5 | Medium
Medicine Delivery Performance Reporting | US-RA-05 | As a pharmacy representative, I want to generate medicine delivery performance reports so that delivery efficiency can be evaluated. | Medicine delivery performance reports are generated accurately. | 5 | Medium